## Sheet1
Status | WBS# | task | Responsible | duration | Start | End | Predecessor | Comment
done | 1 | Set BPB 2010 Goals | BPB | 261 days? | 2010-01-01 08:00 | 2010-12-31 17:00
done | 1.1 | Formally Define BPB 2010 Goals | BPB | 36 days? | 2010-01-01 08:00 | 2010-03-05
done | 1.1.1 | BPB Approval of 2010 Goals | KM/DN | 30 days? | 2010-01-01 08:00 | 2010-02-11 17:00
done | 1.1.2 | Forward Completed Goals to BOD and ISC | KM/DN | 7 days? | 2010-02-11 08:00 | 2010-03-30
| 1.2 | GOAL#1: Shift WG focus to a “practices” perspective, but continue to generate “best practices” where appropriate | TA, PM, RP | 31 days? | 2010-03-11 08:00 | 2010-05-22
| 1.2.1 | FRTA Development | TAPWG
Started | 1.2.1.1 | Complete UML Modeling | TAPWG |  | 2010-03-01 08:00 | 2010-06-30 08:00
| 1.2.21.2 | Integrate UML Model into Requirements | TAPWG |  | 2010-06-30 08:00 | 2010-07-30
| 1.2.1.2 | Develop New FRTA 2.0 Documentation | TAPWG |  | 2010-07-30 | 2010-08-30
| 1.2.21.3 | Develop Conformance Suite | TAPWG |  | 2010-09-01 | 2010-10-31
| 1.2.1.3 | Initial testing of FRTA | TAPWG |  | 2010-10-31 | 11/31/2010
| 1.2.21.4 | Release FRTA for Public Comment | TAPWG |  | 2010-09-30 | 2010-09-10
| 1.2.2 | Create Compliance Document for Extra-Financials | TAPWG
| 1.2.2.1 | Create UML Modeling | TAPWG |  | 2010-10-31 | 2010-12-31 |  | Task will start in 2010 if FRTA is completed
| 1.2.2.2 | Integrate UML Model into Requirements | TAPWG |  | 2010-11-01 | 2010-12-15 |  | Task will start in 2010 if FRTA is completed
| 1.2.2.3 | Develop New document | TAPWG |  | 2011-01-01 | 2011-06-01 |  | Task will start in 2010 if FRTA is completed
| 1.2.2.4 | Develop Conformance Suite | TAPWG |  | 2011-06-01 | 2011-07-30 |  | Task will start in 2010 if FRTA is completed
| 1.2.2.5 | Initial testing of architecture | TAPWG |  | 2011-07-30 | 2011-09-30 |  | Task will start in 2010 if FRTA is completed
| 1.2.2.6 | Release for Public Comment | TAPWG |  | 2011-09-30 | 2010-11-30 |  | Task will start in 2010 if FRTA is completed
| 1.2.3 | Project Manager FAQs | PMPWG
| 1.2.3.1 | Develop Initial Listing | PMPWG |  | 2010-03-01 08:00 | 2010-06-01 08:00
| 1.2.3.2 | Reach Out To PMs World Wide | PMPWG |  | 2010-06-01 08:00 | 2010-08-01
| 1.2.3.3 | Analyze Responses | PMPWG |  | 2010-09-01 | 2010-10-01
| 1.2.3.4 | Generate New FAQ | PMPWG |  | 2010-11-01 | 2010-11-15 08:00
| 1.2.3.5 | Publish To XII Web Site | PMPWG |  | 2010-11-30 | 2010-12-10
| 1.2.4 | Develop Project Managers Checklist | PMPWG
| 1.2.4.1 | Develop Requirements Document | PMPWG |  | 2010-04-01 | 2010-08-01
| 1.2.4.2 | Scope | PMPWG |  | 2010-08-01 | 2010-08-30
| 1.2.4.3 | Goals | PMPWG |  | 2010-08-30 | 2010-09-15
| 1.2.4.4 | Information to Be Captured | PMPWG |  | 2010-09-15 | 2010-09-30
| 1.2.4.5 | Implementation Plan | PMPWG |  | 2010-09-30 | 2010-10-15
| 1.2.4.6 | Determine Resources | PMPWG |  | 2010-10-15 | 2010-10-21
| 1.2.4.7 | Implementation | PMPWG |  | 2010-10-22 | 2010-01-15
| 1.3 | GOAL#2: Lead the collection of market practices and organize on XII web site | PM, XII |  | 2010-01-01 08:00 | 2010-06-25 17:00
| 1.3.1 | interview with project managers, jurisdev and people who intend to implement XBRL regarding what information is useful | PM, XII |  | 2010-05-01 | 2010-05-25
| 1.3.2 | design template for project information | PM, XII |  | 2010-05-01 | 2010-05-25
| 1.3.3 | fit-gap current information versus new template | PM, XII |  | 2010-05-25 | 2010-05-30
| 1.3.4 | design process to capture project information from the market without heavy workload | PM, XII |  | 2010-06-30 | 2010-07-30
| 1.3.5 | start capturing market information | PM, XII |  | 2010-07-30 | 2010-08-30
| 1.3.6 | Event: International Conference | PM, XII |  | 2010-10-10 | 2010-10-10
| 1.3.7 | Evaluate performance | PM, XII |  | 2010-11-05 | 2010-11-05
| 1.4 | GOAL#3: Fine-tune the taxonomy recognition process to meet market demands | TRTF |  | 2010-01-01 08:00 | 2010-07-30 17:00
started | 1.4.1 | TRTF Approval of TR Requirements Plan | TRTF |  | 2010-03-10 | 2010-06-08
| 1.4.2 | BPB Approval TR Requirements Plan | TRTF |  | 2010-06-11 | 2010-06-15
| 1.4.3 | ISC Approval of Requirement Plan | TRTF |  | 2010-06-18 | 2010-07-18
| 1.4.4 | Develop New Assertions | TRTF |  | 2010-06-11 | 2010-08-30
| 1.4.5 | Contract Technical Resources | TRTF |  | 2010-06-11 | 2010-07-11
| 1.4.6 | Develop and Document Additional "Validated" Assertions | TRTF |  | 2010-06-01 | 2010-06-15
| 1.4.7 | Develop and Document Additional "Recognized" Assertions | TRTF |  | 2010-06-16 | 2010-07-01
| 1.4.8 | Develop and Document Additional "Established" Assertions | TRTF |  | 2010-07-02 | 2010-07-30
| 1.4.9 | Develop Requirements for "Certified Taxonomy Developer" | TRTF |  | 2010-07-30 | 2010-08-15
| 1.4.10 | Update TRP To Include New Requirements | TRTF |  | 2010-08-16 | 2010-09-01
| 1.4.11 | Create Marketing Plan | TRTF |  | 2010-03-08 | 2010-06-08
| 1.4.12 | Contract with Marketing Resource | TRTF |  | 2010-03-01 | 2010-06-08
Complete | 1.4.13 | Define Target Audience | TRTF |  | 2010-03-01 | 2010-03-12
Complete | 1.4.14 | Define Marketing Strategy | TRTF |  | 2010-03-19 | 2010-03-26
| 1.4.15 | Develop marketing materials | TRTF |  | 2010-03-29 | 2010-08-16
| 1.4.16 | Update Web Site | TRTF |  | 2010-08-19 | 2010-10-03
| 1.4.17 | Accomplish outreach per plan | TRTF |  | 2010-10-04 | 2010-11-04
| 1.4.18 | Final Approvals | TRTF |  | 2010-11-04 | 2010-11-05
| 1.4.20 | BPB Approval of Marketing/New Taxonomy Recognition Program | TRTF |  | 2010-06-15 | 2010-06-21
| 1.4.22 | Implement Plan | TRTF |  | 2010-11-05 | 2010-11-05
| 1.4.23 | Accomplish Marketing Plan Actions | TRTF |  | 2010-06-01 | 2010-06-07
| 1.4.24 | Release new TRP Document | TRTF |  | 2010-06-01 | 2010-06-07
| 1.5 | GOAL#4: Develop XBRL value proposition document based on common business reporting processes | RPPWG | nnn days | 2010-06-01 08:00 | 2010-10-22 17:00
| 1.5.1 | Develop Introductory XBRL Materials | RPPWG
| 1.5.1.1 | Develop Requirements Document | RPPWG |  | 2010-05-15 | 2010-06-15
| 1.5.1.2 | Scope | RPPWG |  | 2010-06-15 | 7/30/201
| 1.5.1.3 | Goals | RPPWG |  | 2010-07-30 | 2010-08-06
| 1.5.1.4 | Information to Be Captured | RPPWG |  | 2010-08-06 | 2010-08-15
| 1.5.1.5 | Implementation Plan | RPPWG |  | 2010-08-15 | 8/30/201
| 1.5.1.6 | Determine Resources | RPPWG |  | 2010-09-01 | 2010-09-15
| 1.5.1.7 | Implementation | RPPWG |  | 2010-09-15 | 2010-10-31
| 1.5.2 | Develop value proposition document | RPPWG | 2010-06-01 08:00 | 2010-06-01 08:00 | 2010-10-22 17:00
started | 1.5.2.1 | Develop Requirements Document | RPPWG | 104 days? | 2010-06-01 08:00 | 2010-10-22 17:00
| 1.5.2.1.1 | Scope | RPPWG | 6 days? | 2010-06-01 08:00 | 2010-06-08 17:00
| 1.5.2.1.2 | Goals | RPPWG | 1 day? | 2010-06-09 08:00 | 2010-06-09 17:00
| 1.5.2.2 | Information to Be Captured | RPPWG | 6 days? | 2010-06-16 08:00 | 2010-06-23 17:00
| 1.5.2.3 | Implementation Plan | RPPWG | 6 days? | 2010-06-23 08:00 | 2010-06-30 17:00
| 1.5.2.4 | Determine Resources | RPPWG | 60 days? | 2010-07-05 08:00 | 2010-09-24 17:00
| 1.5.2.5 | Implementation | RPPWG | 1 day? | 2010-10-22 08:00 | 2010-10-22 17:00
| 1.5.3 | Evaluate performance | RPPWG
| 1.6 | GOAL#5: Establish a social networking mechanism to exchange latest information on XBRL | XII | 216 days? | 2010-03-05 08:00 | 2010-12-31 17:00
done | 1.6.1 | Develop terms and conditions | Koizumi, XII | 2weeks | 2010-03-05 08:00 | 2010-12-31 17:00
done | 1.6.2 | share idea with ISC and Jurisdev | Koizumi, XII | 2weeks | 2010-03-05 08:00 | 2010-03-26 17:00 | 1.6.1
done | 1.6.3 | Hire initial members | BPB | 30days | 2010-04-02 08:00 | 2010-04-02 17:00 | 1.6.2
done | 1.6.4 | Setup group in LinkedIn | XII | 1day | 2010-04-02 08:00 | 2010-04-09 17:00 | 1.6.2
done | 1.6.5 | Link from XII Web site | XII | 1day | 2010-04-09 08:00 | 2010-04-16 17:00 | 1.6.4
done | 1.6.6 | Public announcement | XII | 1day | 2010-04-16 08:00 | 2010-04-30 17:00 | 1.6.5
| 1.7 | BPB 2010 Formal Goals Complete | - | 0 days | 2010-12-31 08:00 | 2010-12-31 17:00 | 1.6.6
| 1.8 | Evaluate Results
| 2 | Other BPB Tasks |  | 261 days? | 2010-01-01 08:00 | 2010-12-31 17:00
done | 2.1 | Recruit replacement WG chairs for Taxonomy Architecture Practice Working Group (TAPWG). | DN KM BPB | 57 days? | 2010-02-11 08:00 | 2010-04-30 17:00
| 2.2 | Recruit replacement WG chairs for Project Management Practice Working Group (PMPWG). | DN KM BPB | 57 days? | 2010-02-11 08:00 | 2010-04-30 17:00
done | 2.3 | Create Combine BPB and WG Goals Document | DN | 7 days? | 2010-02-25 08:00 | 2010-03-05 17:00
| 2.4 | Increase the volunteer base of BPB working groups. | DM | 16 days? | 2010-05-25 | 2010-04-16 17:00
| 2.5 | Define position descriptions for potential volunteers. | DM | 11 days? | 2010-03-26 08:00 | 2010-06-09 17:00
| 2.6 | Recruit volunteers. | XII | 6 days? | 2010-04-09 08:00 | 2010-06-16 17:00
| 2.7 | Identity discrete tasks that can be accomplished by academic community. | XII | 6 days? | 2010-04-09 08:00 | 2010-06-16 17:00
| 2.8 | Contract outside resources to improve BPB output. | XII | 60 days? | 2010-01-01 08:00 | 2010-10-25 17:00
| 2.9 | Identify tasks, which can be accelerated by use of a contract technical writer. | XII | 60 days? | 2010-01-01 08:00 | 2010-07-25 17:00
| 2.10 | Updated Case Studies (at least at each international conference: twice a year) | XII | 227 days? | 2010-02-18 08:00 | 2010-12-31 17:00
| 3 | PWG Tasks
done | 3.1 | Develop formal document containing BPB and BPB Working Groups (WG) 2010 goals. This document will contain: | DN KM BPB | 46 days? | 2010-01-01 08:00 | 2010-03-05 17:00
done | 3.1.1 | BPB 2010 Goals | DN KM BPB | 30 days? | 2010-01-01 08:00 | 2010-02-11 17:00